## HOSPITAL INFORMATION
Please enter your hospital information on this page before completing any other tabs! |  | Project Resources List
MSQC 2023 QI Initiatives web page
American Society of Anesthesiologists’ “Choosing Wisely” program
United Kingdom’s NICE (National Institute for Health and Care Excellence)
Drop the Preop Toolkit (Choosing Wisely Canada)
Drop the Preop! Information Sheet (Washington State Task Force)
Appropriate Preoperative Screening for Low-Risk Surgeries educational slide deck
Hospital Name: | <Enter your hospital's name here>
Project Submitter Name: | <Enter your name here>
HOSPITAL INFORMATION

## Roadmap to Implementation
Hospital Name: | <Enter your hospital's name here>
Project Submitter Name: | <Enter your name here>
Implementation Roadmap to help guide project rollout at your hospital
Step 2: Make a plan
Step 1: Prepare your hospital
Review Project
Review the project description, goals, and related documentation
Identify existing protocols
Become familiar with industry-supported preoperative screening protocols, including any existing protocol in use at your facility
Obtain hospital data reports
Obtain copies of your hospital's existing MVC preoperative screening reports previously sent to your site's MVC Site Coordinator
Collect baseline project data
Begin collecting baseline project data on eligible cases
Select the team
Identify the members of your project team
Project kickoff
Host your initial multi-disciplinary team meeting by March 31, 2023
Step 3: Educate and Implement
Select a protocol
Select an industry-standard or develop a proprietary preoperative screening protocol to implement
Perform gap analysis
Perform gap analysis, apply QI methodology to compare hospital current state with desired state necessary for adoption of preoperative screening protocol
Review MVC data reports
Review MVC preoperative screening reports to identify trends and gain insight into routine preoperative screening patterns for low-risk surgeries
Identify areas of focus
Apply findings from gap analysis/other sources to prioritize processes, education, resources needed for project implementation
Promote protocol
Promote protocol to gain awareness and knowledge with physicians
Develop or adopt materials
Develop project materials or adopt/adapt existing educational materials from professional practice organizations
Educate providers/staff
Educate physicians as well as surgery department and surgeon office staff
Implement CDS tools, processes
Implement clinical decision support (CDS) tools and related processes to integrate the preoperative testing protocol into physician practice
Step 4: Evaluate
Data collection
Ensure adequate data collection by abstracting all eligible cases
Share data findings
Share findings of project progress with providers, physician leaders, and project team.
Monitor project progress
Monitor progress of protocol implementation and effectiveness
Modify/revise processes
Apply findings of data monitoring to modify processes in order to maintain and improve adoption of protocol
Re-convene project team
Host second multi-disciplinary team between July and December 2023
Data report feedback
Provide brief feedback regarding the value of MVC and MSQC data reports and how the data was utilized
Survey participation
Participate in MPrOVE qualitative survey if asked
Final QI project summary
Submit QI project summary to MSQC by January 16, 2024
HOSPITAL INFORMATION

## Step 1-Prepare Hospital
Hospital Name: | <Enter your hospital's name here>
Project Submitter Name: | <Enter your name here>
*denotes a deliverable due with final project submission
Item | Item Details | Activities Tracking: Examples (not all-inclusive): Dates, meetings, materials developed, communications with multidisciplinary team members, any teaching done with staff/patients, meeting notes (or attach separately)
Review the project goals | Work toward reducing unnecessary, routine preoperative testing for low-risk surgeries Review the Appropriate Preoperative Screening for Low-Risk Surgeries Pilot Study project description (available on MSQC Quality Initiatives web page) Review JAMA article on preoperative testing patterns for additional information: https://jamanetwork.com/journals/jamainternalmedicine/fullarticle/2779744
Become familiar with existing preoperative screening protocols | American Society of Anesthesiologists’ “Choosing Wisely” program (https://www.choosingwisely.org/clinician-lists/american-society-anesthesiologists-baseline-laboratory-studies-for-low-risk-surgery) United Kingdom’s NICE (National Institute for Health and Care Excellence) preoperative testing guidelines for elective surgery (https://www.nice.org.uk/guidance/ng45) Your own hospital preoperative testing protocol (if one currently exists)
Obtain existing hospital data reports | Obtain your hospital's MVC Preoperative Testing Reports Hospital preoperative testing reports distributed: • February 2021 (all payers) • December 2021 (BCBSM/BCN only) • April 2022 (all payers) • July 2022 (BCBSM/BCN only Sytem-level preoperative testing report distributed: • December 2021 (BCBSM/BCN only) • April 2022 (all payers) • August 2022 (BCBSM/BCN only)
Baseline project data | Begin abstracting baseline project data beginning with January 1, 2023 cases Baseline time period: 1/1/2023 - 3/31/2023
Identify your project team members | Required members: • Anesthesiologist • General surgeon • MSQC/Quality department representation Additional recommended members: • Hospital's Michigan Value Collaborative (MVC) Site Coordinator • Primary care provider (PCP) • OB/GYN surgeon • Preoperative clinic manager/staff • Surgical resident or • Physician office staff • Clinical Informatics staff • Hospital/corporate IT contact Select person to serve as Appropriate Preoperative Screening Pilot Study POC with MVC, and submit that person's contact information to MSQC no later than April 14, 2023
Multi-disciplinary kickoff meeting* (Goal #3a) | Host meeting with key stakeholders by March 31, 2023 to review project requirements. Designate person to serve as Appropriate Preoperative Screening Pilot Study Point of Contact. (provide name/title to MSQC by 4/14/2023)
Step 1: Prepare your hospital
HOSPITAL INFORMATION
Note on C12: Excel Tip: For a carriage return (new line) in a cell, use Alt+Enter keyboard shortcut
Note on A18: Deliverable: Must submit a copy of meeting minutes, agenda, and attendee list with your final project summary.

## Step 2-Make a Plan
Hospital Name: | <Enter your hospital's name here>
Project Submitter Name: | <Enter your name here>
*denotes a deliverable due with final project submission
Item | Item Details | Activities Tracking: Examples (not all-inclusive): Dates, meetings, materials developed, communications with multidisciplinary team members, any teaching done with staff/patients, meeting notes (or attach separately)
Select a protocol for implementation* at your hospital (Goal #2a) | Select a protocol and implement it at your hospital no later than June 30, 2023 • American Society of Anesthesiologists’ “Choosing Wisely” program • United Kingdom’s NICE (National Institute for Health and Care Excellence) preoperative testing guidelines for elective surgery • Review and modify an existing internally-developed protocol already in use at your hospital • Develop your own hospital preoperative testing protocol
Insight from MVC data reports | Review existing MVC Preoperative Testing Reports to determine if any trends or issues can be gleaned (certain procedures higher than others, specific surgeon differences, etc.)
Perform gap analysis | Perform a gap analysis and apply QI methodology to identify your hospital's current processes/resources, as compared to where you need be for the project to be successful. Example items (not all-inclusive): • Practitioner awareness/knowledge of and support for proposed protocol • Hospital/surgeon office staff familiarity with protocol (e.g., pre-surgical testing clinic, surgical boarding office, etc.) • Existence of any clinical decision support tools for promoting compliance with protocol • Infrastructure support to create/implement clinical decision support tools (such as IT resources, informatics, EMR functionality to support use of tools, etc.) • Existing preoperative order sets, care pathways in concurrence with new protocols? • Consistencies or differences between hospital and individual surgeon office EMRs (how many surgeons place preop orders directly into hospital EMR vs. their own electronic or paper ordering processes?)
Determine areas of focus | Use findings from gap analysis and other sources to identify processes, education, and resources that will need to be put into place.
Step 2: Make a Plan
HOSPITAL INFORMATION
Note on C12: Excel Tip: For a carriage return (new line) in a cell, use Alt+Enter keyboard shortcut
Note on A13: Deliverable: Must submit a copy of your selected protocol with your final project summary.

## Step 3-Educate & Implement
Hospital Name: | <Enter your hospital's name here>
Project Submitter Name: | <Enter your name here>
*denotes a deliverable due with final project submission
Item | Item Details | Activities Tracking: Examples (not all-inclusive): Dates, meetings, materials developed, communications with multidisciplinary team members, any teaching done with staff/patients, meeting notes (or attach separately)
Promote protocol concepts and benefits with physicians | Use opinion leaders among physician staff to promote awareness and knowledge of protocol and to gain buy-in, such as: • Chief medical officer • Director of medical education • Department chairs of surgery, anesthesia, primary care
Develop and/or adopt educational materials | Take advantage of existing educational materials available from professional practice organizations; review/adopt/adapt to fit your hospital's needs Develop your own project materials
Educate physicians on protocol | Present information at medical department meetings If teaching facility, present protocol at surgery/anesthesia resident meetings and new resident orientation sessions Provide educational materials, pocket cards
Educate surgery department and surgeon office staff on protocol | Educate staff where preoperative workup orders are placed/processed: • surgeon offices • preoperative clinic • surgery boarding office
Implement processes and clinical decision support tools* to incorporate protocol into provider practice (Goal #2b) | Implement processes and clinical decision support tools: • Order sets • Care pathways • CPOE pop-up messages/suggestions • BPA (Best Practice Advisory) Perform a documented inventory indicating review of existing order sets for concurrence with adopted testing guidelines
Step 3: Educate and Implement
HOSPITAL INFORMATION
Note on C12: Excel Tip: For a carriage return (new line) in a cell, use Alt+Enter keyboard shortcut
Note on A17: Deliverable: Must submit an example of at least one clinical decision support tool that was implemented at your hospital with your final project summary.

## Step 4-Evaluate
Hospital Name: | <Enter your hospital's name here>
Project Submitter Name: | <Enter your name here>
*denotes a deliverable due with final project submission
Item | Item Details | Activities Tracking: Examples (not all-inclusive): Dates, meetings, materials developed, communications with multidisciplinary team members, any teaching done with staff/patients, meeting notes (or attach separately)
Ensure adequate data collection | Track completeness of SCQR case abstraction with MSQC report (goal is at least 80% complete data collection of preop diagnostic testing for eligible procedures)
Monitor project progress | Monitor progress of protocol implementation and effectiveness: • MSQC report for prevalence of routine preoperative screening for low-risk surgeries (goal is at least 20% reduction compared to baseline) • MVC Preoperative Testing Reports (distributed to the Appropriate Preoperative Screening Pilot Study POC and the MVC Site Coordinator) • Any internal hospital data collection for monitoring compliance and adoption of the preoperative testing protocol Share/discuss data findings with team members, other stakeholders
Share data findings | Discuss protocol implementation, progress and barriers to implementation, and monitoring of compliance data (including MVC and MSQC preoperative testing data) with providers, physician leaders, and project team.
Modify/revise processes | Apply findings of data monitoring to identify components and processes of project requiring modification in order to maintain and improve adoption of protocol
Second multi-disciplinary meeting* (Goal #3b) | Convene a second multi-disciplinary meeting between July and December 2023 to: • review project status • discuss protocol implementation • determine trends in project data • identify barriers to implementation • plan strategies to address barriers
Provide data report feedback* (Goal #4) | Sites will include brief feedback regarding the value of the MVC and MSQC data reports and how the data was utilized in the 2023 Appropriate Preoperative Screening Pilot Study Summary. (1 point)
Qualitative survey participation | MPrOVE will conduct qualitative interviews with 8-10 sites throughout the state. Sites must agree to participate in the qualitative survey if they are asked for their feedback.
Submit final QI project summary* | Submit QI project summary to MSQC by January 16, 2024, with a narrative describing: • adoption of protocol • implementation process • data monitoring process and findings • success and barriers to implementation • future project plans • feedback regarding the pilot project experience including suggestions for future on future development of the program. Additional documents to be submitted with the summary include: • Copy of the preoperative testing protocol for low-risk surgery adopted by your facility (from Goal #2a) • Example of at least one clinical decision support tool that was implemented at your site (from Goal #2b) • Meeting documents (minutes, participant list) from the project kickoff and subsequent follow-up multidisciplinary meetings held during the project year (from Goal #3) • Feedback on the MVC and MSQC data reports (from Goal #4)
Step 4: Evaluate
HOSPITAL INFORMATION
Note on C12: Excel Tip: For a carriage return (new line) in a cell, use Alt+Enter keyboard shortcut
Note on A17: Deliverable: Must submit a copy of meeting minutes, agenda, and attendee list with your final project summary.
Note on A18: Deliverable: Must submit feedback on MSQC and MVC data reports with your final project summary.
Note on A20: Final project summary deliverable to MSQC

## Quality Measure Tracking
|  | Hospital Name: | <Enter your hospital's name here>
|  | Project Submitter Name: | <Enter your name here>
Project Cohort Definition: o Minor hernia, laparoscopic cholecystectomy, and breast lumpectomy*, AND o Surgical Priority = Elective, AND o Surgical Procedure Tab: Is the CPT code the intended primary procedure= Yes *eligible CPT code list available below
Goal Definition | Variable Requirements | Measurement Period | Goal | Points
Goal 1a: Abstract and capture preoperative diagnostic testing that was performed within 90 days prior to surgery date into the MSQC Workstation. | See Goal 1b variable requirements | 1/1/2023 - 12/31/2023 (cases in Workstation marked Complete (incl. follow-up) as of 1/16/2024) | ≥ 50% of cases in annual denominator for Goal 1b has complete data abstraction | 2
|  | Performance Tracking Grid | (for your own use; you are not required to track your data here)
|  | Tracking Time Period | Numerator | Denominator | Rate (%)
|  | Example: January 2023 | 42 | 100 | 42%
Goal Definition | Variable Requirements | Measurement Period | Goal | Points
Goal 1b: Achieve 80% complete data collection of preop diagnostic testing performed within 90 days preoperatively for eligible procedures. | Screening tab: Case documentation includes all of the following on all 9 diagnostic test categories*: 1. Presence/absence of diagnostic test in EMR AND, if test was performed: 2. Date diagnostic test was performed | 1/1/2023 - 12/31/2023 (cases in Workstation marked Complete (incl. follow-up) as of 1/16/2024) | ≥ 80% | 4
|  | Performance Tracking Grid | (for your own use; you are not required to track your data here)
|  | Tracking Time Period | Numerator | Denominator | Rate (%)
|  | Example: January 2023 | 42 | 100 | 42%
Goal Definition | Variable Requirements | Measurement Period | Goal | Points
Goal 2c: Achieve measurable progress toward reducing the use of low-value preoperative testing within 30 days prior to surgery by 20% as compared to baseline rate (5 points) | Screening tab: Eligible project case received at least one or more of the following preoperative diagnostic tests in the 30 days prior to surgery* date: *excludes tests performed on day of surgery | 4/1/2023 - 12/31/2023 (cases in Workstation marked Complete (incl. follow-up) as of 1/16/2024) | ≥ 20% reduction as compared to baseline rate "Less is better" measure | 5
|  | Performance Tracking Grid | (for your own use; you are not required to track your data here)
|  | Tracking Time Period | Numerator | Denominator | Rate (%)
|  | Example: January 2023 | 42 | 100 | 42%
Open Inguinal/Femoral/Umbilical & All Laparoscopic Hernia Repairs ("Minor Hernia")
49505: Repair initial inguinal hernia, age 5 years or older; reducible. | 49585: Repair umbilical hernia, age 5 years or older; reducible.
49507: Repair initial inguinal hernia, age 5 years or older; incarcerated or strangulated. | 49587: Repair umbilical hernia, age 5 years or older; incarcerated or strangulated.
49520: Repair recurrent inguinal hernia, any age; reducible. | 49650: Laparoscopy, surgical; repair initial inguinal hernia.
49521: Repair recurrent inguinal hernia, any age; incarcerated or strangulated. | 49651: Laparoscopy, surgical; repair recurrent inguinal hernia.
49525: Repair inguinal hernia, sliding, any age. | 49652: Laparoscopy, surgical, repair, ventral, umbilical, spigelian or epigastric hernia; reducible.
49550: Repair initial femoral hernia, any age; reducible. | 49653: Laparoscopy, surgical, repair, ventral, umbilical, spigelian or epigastric hernia; incarcerated or strangulated
49553: Repair initial femoral hernia, any age; incarcerated or strangulated. | 49654: Laparoscopy, surgical, repair, incisional hernia; reducible.
49555: Repair recurrent femoral hernia; reducible. | 49655: Laparoscopy, surgical, repair, incisional hernia; incarcerated or strangulated.
49557: Repair recurrent femoral hernia; incarcerated or strangulated. | 49656: Laparoscopy, surgical, repair, recurrent incisional hernia; reducible.
49570: Repair epigastric hernia; reducible. | 49657: Laparoscopy, surgical, repair, recurrent incisional hernia; incarcerated or strangulated.
49572: Repair epigastric hernia; incarcerated or strangulated. | 49659: Unlisted laparoscopy procedure, hernioplasty, herniorrhaphy, herniotomy.
Laparoscopic Cholecystectomy
47562: Laparoscopy, surgical; cholecystectomy
47563: Laparoscopy, surgical; cholecystectomy with cholangiography
47564: Laparoscopy, surgical; cholecystectomy with exploration of common duct
Breast Lumpectomy/Partial Mastectomy
19301: Mastectomy, partial (e.g., lumpectomy, tylectomy, quadrantectomy, segmentectomy)
Quality Measure Definitions, Goals, and Tracking
HOSPITAL INFORMATION

## Final Project Summary
Hospital Name: | <Enter your hospital's name here>
Project Submitter Name: | <Enter your name here>
Item | Item Details | Final Summary
Multi-disciplinary kickoff meeting (Goal #3a) | Host meeting with key stakeholders by March 31, 2023 to review project requirements. Submit agenda, minutes, participant list (name, title/role, department affiliation) | <Enter information here, or insert file(s)>
Select a protocol for implementation at your hospital (Goal #2a) | Submit a copy of the protocol adopted by your hospital | <Enter information here, or insert file(s)>
Implement processes and clinical decision support tools to incorporate protocol into provider practice (Goal #2b) | Implement processes and clinical decision support tools: • Order sets • Care pathways • CPOE pop-up messages/suggestions • BPA (Best Practice Advisory) Perform a documented inventory indicating review of existing order sets for concurrence with adopted testing guidelines | <Enter information here, or insert file(s)>
Second multi-disciplinary meeting (Goal #3b) | Convene a second multi-disciplinary meeting between July and December 2023 to: • review project status • discuss protocol implementation • determine trends in project data • identify barriers to implementation • plan strategies to address barriers Submit agenda, minutes, participant list (name, title/role, department affiliation) | <Enter information here, or insert file(s)>
Provide data report feedback (Goal #4) | Include brief feedback regarding the value of the MVC and MSQC data reports and how the data was utilized in the 2023 Appropriate Preoperative Screening Pilot Study Summary. | <Enter information here>
Submit final QI project summary | Submit QI project summary to MSQC by January 16, 2024, with a narrative describing: • adoption of protocol • implementation process • data monitoring process and findings • success and barriers to implementation • future project plans • feedback regarding the pilot project experience including suggestions for future on future development of the program. | <Enter information here>
Goal #6: Submit Final Project Summary (due January 16, 2024)
HOSPITAL INFORMATION
Note on C12: Excel Tip: For a carriage return (new line) in a cell, use Alt+Enter keyboard shortcut

## General PI Measure Monitoring
|  | Hospital Name: | <Enter your hospital's name here>
|  | Project Submitter Name: | <Enter your name here>
Goal Definition | Variable Requirements | Measurement Period | Goal | Points
Collaborative-Wide Measure (CWM) Reduce the percentage of all MSQC elective procedures* performed on patients who have smoked within the last 30 days prior to surgery *Excludes patients with disseminated cancer | Preop Tab: Tobacco Use within 1 month – Cigarette= Yes ("Less is better" measure) | 1/1/2023 - 12/31/2023 (cases in Workstation marked Complete (incl. follow-up) as of 1/16/2024) | "MSQC-All" Goal* ≤ 13.9%: 20 points 14.0% - 14.4%: 15 points 14.5% - 15.0%: 10 points 15.1% - 15.6%: 5 points ≥ 15.7%: 0 points *Goal may be updated when additional 2022 data available | 0 - 20 points available, depending on collaborative-wide performance
|  | Performance Tracking Grid | (for your own use; you are not required to track your data here)
|  | Tracking Time Period | Numerator | Denominator | Rate (%)
|  | Example: January 2023 | 42 | 100 | 42%
Goal Definition | Variable Requirements | Measurement Period | Goal | Points
Completeness of Hernia* Documentation Complete documentation of size and location of hernia ≥ 90% Hernia documentation includes: • hernia measurements • hernia location *Abdominal hernias only; excludes intraoperative death | Hernia tab: Documentation of hernia includes all (both) of the following: 1. Hernia size length AND width (valid non-zero measurements) entered, OR diameter (valid non-zero measurement) entered AND 2. Hernia Location entered (<> "Not Documented") | 1/1/2023 - 12/31/2023 (cases in Workstation marked Complete (incl. follow-up) as of 1/16/2024) | ≥ 90% | 5
Abdominal Hernia CPT Codes
49560: Repair initial incisional or ventral hernia; reducible |  | Performance Tracking Grid | (for your own use; you are not required to track your data here)
49561: Repair initial incisional or ventral hernia; incarcerated or strangulated |  | Tracking Time Period | Numerator | Denominator | Rate (%)
49565: Repair recurrent incisional or ventral hernia; reducible |  | Example: January 2023 | 42 | 100 | 42%
49566: Repair recurrent incisional or ventral hernia; incarcerated or strangulated
49570: Repair epigastric hernia; reducible
49572: Repair epigastric hernia; incarcerated or strangulated
49585: Repair umbilical hernia, age 5 years or older; reducible
49587: Repair umbilical hernia, age 5 years or older; incarcerated or strangulated. CPT includes mesh.
49590: Repair spigelian hernia
49652: Laparoscopy, surgical, repair, ventral, umbilical, spigelian or epigastric hernia; reducible
49653: Laparoscopy, surgical, repair, ventral, umbilical, spigelian or epigastric hernia; incarcerated or strangulated
49654: Laparoscopy, surgical, repair, incisional hernia; reducible
49655: Laparoscopy, surgical, repair, incisional hernia; incarcerated or strangulated
49656: Laparoscopy, surgical, repair, recurrent incisional hernia; reducible
49657: Laparoscopy, surgical, repair, recurrent incisional hernia; incarcerated or strangulated
Goal Definition | Variable Requirements | Measurement Period | Goal | Points
Sampled and Incomplete Cases ≤ 0.5% All MSQC-eligible procedures (Program Manual Appendix A) AND Case Listing: Case Status = Sampled AND Case Listing: Current date > Lock Date Measure calculated using locked cases only | Case Admin Tab: Case Completed? variable <> "Case abstraction complete including 30 day follow-up" Can also track alternately using Workstation Case List "Complete Status" field = No | Cycle 33-2022 through Cycle 32-2023 | ≤ 0.5% total volume ("Less is better" measure) | 3
|  | Performance Tracking Grid | (for your own use; you are not required to track your data here)
|  | Tracking Time Period | Numerator | Denominator | Rate (%)
|  | Example: January 2023 | 42 | 100 | 42%
Goal Definition | Variable Requirements | Measurement Period | Goal | Points
30 Day Follow-Up Rate 30 day follow-up rate ≥ 80% for each of the first 3 calendar quarters of 2023 Case Listing: Case Status = Sampled AND Case Listing: Complete Status = Yes* *based on Case Admin Tab: Case Completed? = Case abstraction complete including 30 day follow-up | Case Listing: Follow Up Status = Yes* *Follow Up Status = Yes is defined as: • Follow Up Tab: Was 30 day clinical follow up obtained? = Yes AND • Follow Up Tab: Did you attempt to contact the patient 3 times or until they responded, whichever comes first? = Yes or Not applicable | Q1 2023 (Jan - March) Q2 2023 (April - June) Q3 2023 (July - Sept) | ≥ 80% per quarter | 1 point for each quarter where goal is met
|  | Performance Tracking Grid | (for your own use; you are not required to track your data here)
|  | Tracking Time Period | Numerator | Denominator | Rate (%)
|  | Example: January 2023 | 42 | 100 | 42%
HOSPITAL INFORMATION

## Site-Directed Measure Tracking
|  | Facility Name: | <Enter your hospital's name here>
|  | Submitted By: | <Enter your name here>
Goal Definition | Variable Requirements | Time Periods | Goal | Points
Specific measure defined by site. Baseline unadjusted rate will be based on data from completed 2022 cases in the Workstation as of 1/16/2023. | Specific measure defined by site. Describe exact parameters used to calculate measure numerator and denominator. | Baseline Period: 2022 cases (2022 cases in Workstation marked Complete as of 1/16/2023) Measurement Period: 1/1/2023 - 12/31/2023 (cases in Workstation marked Complete (incl. follow-up) as of 1/16/2024) | Performance improvement over baseline: ≥ 10% = 20 points 7.5-9.99% = 15 points 5-7.49% = 10 points 2.5-4.99% = 5 points < 2.5% = 0 points | 0 - 20 points available, depending on performance
|  | Performance Tracking Grid | (for your own use; you are not required to track your data here)
Baseline Rate: <enter value here>
|  | Tracking Time Period | Numerator | Denominator | Rate (%)
|  | Example: January 2023 | 42 | 100 | 42%
Project Deliverables | Project Deliverable Details
Describe selected measure: What outcome measure was chosen? What procedure group will be included? | Outcome Measure Description: <enter description here> Procedure Groups Included in Measure: <enter included procedure group listing here>
Define measure denominator parameters: What population is included in the denominator? (Example: All MSQC procedures or all colectomy patients) | <enter measure denominator population here>
Define measure numerator parameters: What population is included in the numerator? (Example: Return to ED related to surgery) | <enter measure numerator population here>
Document measure baseline rate: Baseline Period: all completed 2022 cases available in the Workstation as of 12/19/2022. MSQC will pull data on this date and send to sites in January. (You can also run your baseline data in the Workstation on 12/19/2022) | <enter measure baseline rate here>
Category | Activity/Category Details
Activities Examples (not all-inclusive): Dates; meetings; materials developed; preop and postop education materials; communications with multidisciplinary team members; any teaching done with staff | <enter information here>
Successes Example questions: What has your hospital improved on? What are you most proud of? | <enter information here>
Barriers and Challenges Example questions: What prevented you from improving more? What would you like see changed? | <enter information here>
Analysis /Next Steps Example questions: What are the next steps in your quality improvement efforts? What are your hospitals plans for moving forward with these changes? | <enter information here>
Note on B26: Excel Tip: To insert a carriage return (new line) in the cell, press Alt+Shift.
Note on B32: Excel Tip: To insert a carriage return (new line) in the cell, press Alt+Shift.